## Execution Summary
CertiSphere — Test Execution Summary Report
Project: Certisphere (CS1) · Prepared by: G. Pravalika · Executed/Fixed by: Development · Execution date: 11-07-2026
Test Case ID | Objective | Area | Before (Iter 0) | After (Iter 1) | Resolution Notes
TC_CS_1.1 | Login validation on module click | Home | Fail | Pass | Module cards route to Login with intent notice; auto sign-in removed
TC_CS_1.2 | Certification body auth context | Home | Fail | Pass | Cert-body click passes "Sign in to access" context to Login banner
TC_CS_1.3 | Company Profile availability | Home | Fail | Pass | Company Profile button live in About Us founder card
TC_CS_1.4 | Contact details display | Home | Fail | Pass | Phone, email, address shown with high contrast; address opens Google Maps
TC_CS_1.5 | Country flags display | Home/Login | Fail | Pass | Inline SVG flags beside names, full colour, no network dependency
TC_CS_1.6 | Get Started / Explore Modules buttons | Home | Fail | Pass | Get Started → Login; Explore Modules → scrolls to Modules
TC_CS_1.7 | Section text visibility | Home | Fail | Pass | Readability pass: 80%+ cream, larger sizes and line-height
TC_CS_1.8 | Duplicate logo / Sign In | Home | Fail | Pass | Showcase band removed; single header Sign In
TC_CS_1.9 | Contact form layout | Home | Fail | Pass | Modal exempted from dark theme; dark labels on white
TC_CS_1.10 | Founder photo empty space | Home | Fail | Pass | Instant RC monogram; photo auto-loads when file added
TC_CS_1.11 | Founder buttons navigation | Home | Fail | Pass | Company Profile → website; Get In Touch → contact form
TC_CS_1.12 | Logo clarity | Login | Fail | Pass | 3260px HD source + sharpening filter
TC_CS_1.13 | Enquiry heading visibility | Login/Enquiry | Fail | Pass | Explicit white heading + text shadow
TC_CS_1.14 | Login box contrast | Login | Fail | Pass | Contrast raised on all labels, chips, inputs
TC_CS_1.15 | Login box contrast (dup) | Login | Fail | Pass | Covered by TC_CS_1.14 fix
TC_CS_1.16 | Demo credentials button label | Login | Fail | Pass | "Use" buttons fill the form; explicit Sign In required
Total executed | 16
Passed (Iteration 1) | 16
Failed (Iteration 1) | 0
Pass rate | 100%